## Log Sheet
Day | Date | From | To | Time | Done | Total hours spent | 31:40
Monday | 2022-04-11 | 11:00 | 11:30 | 0:30 | Set up Trello board and initial cards
Monday | 2022-04-11 | 11:30 | 11:45 | 0:15 | Set up log sheet
Tuesday | 2022-04-12 | 10:00 | 12:00 | 2:00 | Setting up Xemu Emulator
Wednesday | 2022-04-13 | 10:00 | 11:00 | 1:00 | Setting up Xemu emulator
Wednesday | 2022-04-13 | 11:00 | 12:00 | 1:00 | Make simple plane model in Maya
Wednesday | 2022-04-13 | 13:30 | 14:30 | 1:00 | Get Xemu emulator to work
Wednesday | 2022-04-13 | 18:35 | 19:30 | 0:55 | Work on basic flight system using character controller
Thursday | 2022-04-14 | 13:00 | 14:00 | 1:00 | Smooth pitch, roll & yaw and stabilize flight
Thursday | 2022-04-14 | 14:00 | 14:30 | 0:30 | Import plane model from Maya
Thursday | 2022-04-14 | 16:30 | 17:15 | 0:45 | Work on primary weapon gunnery rig
Thursday | 2022-04-14 | 19:30 | 20:30 | 1:00 | Work on primary weapon gunnery rig
Thursday | 2022-04-29 | 10:45 | 12:45 | 2:00 | Camera groundwork (Class exercises, different project)
Friday | 2022-04-29 | 15:30 | 16:30 | 1:00 | Camera groundwork (Class exercises, different project)
Friday | 2022-04-29 | 18:00 | 18:45 | 0:45 | Yaw roll
Friday | 2022-04-29 | 19:00 | 20:30 | 1:30 | Boost & Brake
Wednesday | 2022-05-04 | 14:00 | 16:00 | 2:00 | Level selection, research & floorplan creation
Wednesday | 2022-05-04 | 16:00 | 18:00 | 2:00 | Build rough level with Probuilder & Find and insert free water shader
Thursday | 2022-05-05 | 10:45 | 11:30 | 0:45 | Wingtip smoke particle system
Thursday | 2022-05-05 | 11:30 | 12:45 | 1:15 | Primary gunnery system, particles & sound
Thursday | 6691369 | 18:00 | 19:00 | 1:00 | Refine particle system for wing smoke
Friday | 2022-05-06 | 10:00 | 12:00 | 2:00 | Groundwork for AI dogfighting, calculating steering
Friday | 2022-05-06 | 13:30 | 15:00 | 1:30 | AI framework
Friday | 2022-05-06 | 18:00 | 19:00 | 1:00 | Tweaking AI
Saturday | 2022-05-07 | 11:00 | 12:30 | 1:30 | AI firing logic + 1st order intercept
Wednesday | 2022-05-12 | 14:00 | 16:00 | 2:00 | Hit detection + fix sound
Wednesday | 2022-05-12 | 16:00 | 17:30 | 1:30 | Enemy plane model + camera swivel
0:00
0:00
0:00
0:00